## Sheet1
|  | Duration | Start | Finish | Predecessors | Budget | Gantt Chart
| HR Department | 12 days | 2015-12-14 | 2015-02-15 |  | 0$ | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 1 | 2 | 3 | 4 | 5
1 | Plan the essential materials | 1 day | 2015-12-14 | 2015-12-14 | - | 0$ | bar: Gantt Chart 14
2 | Plan the essential labour force | 1 day | 2015-12-14 | 2015-12-14 | - | 0$ | bar: Gantt Chart 14
3 | Request the money for the essential materials from finans department | 1 day | 2015-12-15 | 2015-12-15 | 1 | 10.000$ | bar: Gantt Chart 15
4 | Buy the essential materials | 1 day | 2015-12-17 | 2015-12-17 | 36 | 0$ | bar: Gantt Chart 17
5 | Make job advert | 1 day | 2015-12-15 | 2015-12-15 | 2 | 0$ | bar: Gantt Chart 15
6 | Request 2 people from finans department for interviews | 1 day | 2015-12-15 | 2015-12-15 | 2 | 0$ | bar: Gantt Chart 15
7 | Make interviews | 3 days | 2015-12-17 | 2015-12-21 | 37 | 0$ | bar: Gantt Chart 17 to Gantt Chart 21
8 | Return the 2 people to the finans department | 1 day | 2015-12-22 | 2015-12-22 | 7 | 0$ | bar: Gantt Chart 22
9 | Make recruitment | 1 day | 2015-12-23 | 2015-12-23 | 8 | 0$ | bar: Gantt Chart 23
44 | Give 3 people to Software Department | 1 day | 2015-02-15 | 2015-02-15 | 31 | 0$ | bar: Gantt Chart 15
| Software Department | 58 days | 2015-12-24 | 2015-02-22 |  | 0$
10 | Request 2 people from finans department for research | 1 day | 2015-12-24 | 2015-12-24 | 9 | 0$ | bar: Gantt Chart 24
11 | Request 2 people from hr department for research | 1 day | 2015-12-24 | 2015-12-24 | 9 | 0$ | bar: Gantt Chart 24
12 | Request the money for 7 computer from finans department | 1 day | 2015-12-24 | 2015-12-24 | 9 | 40.000$ | bar: Gantt Chart 24
13 | Buy the computers | 1 day | 2015-12-25 | 2015-12-25 | 39 | 0$ | bar: Gantt Chart 25
14 | research about similar app | 4 days | 2015-12-26 | 2015-12-31 | 13 | 0$ | bar: Gantt Chart 28 to Gantt Chart 31
15 | Return the 2 people to the finans department | 1 day | 2015-01-01 | 2015-01-01 | 14 | 0$ | bar: Gantt Chart 1
16 | Return the 2 people to the hr department | 1 day | 2015-01-01 | 2015-01-01 | 14 | 0$ | bar: Gantt Chart 1
17 | plan system architecture | 1 day | 2015-01-01 | 2015-01-01 | 14 | 0$ | bar: Gantt Chart 1
18 | design the frontend (UI/UX) | 5 days | 2015-01-01 | 2015-01-07 | 14 | 0$ | bar: Gantt Chart 1 to Gantt Chart 7
19 | Create Database | 2 days | 2015-01-01 | 2015-01-04 | 14 | 0$ | bar: Gantt Chart 1 to Gantt Chart 4
20 | Create and test backend functions | 20 days | 2015-01-04 | 2015-01-29 | 17 | 0$ | bar: Gantt Chart 4 to Gantt Chart 29
21 | Connect backend with frontend | 3 days | 2015-02-01 | 2015-02-03 | 18;20 | 0$ | bar: Gantt Chart 1 to Gantt Chart 3
23 | Integration Test | 1 day | 2015-02-04 | 2015-02-04 | 21 | 0$ | bar: Gantt Chart 4
24 | Developer Tests | 2 days | 2015-02-04 | 2015-02-05 | 21 | 0$ | bar: Gantt Chart 4 to Gantt Chart 5
25 | System Test | 2 days | 2015-02-08 | 2015-02-09 | 24 | 0$ | bar: Gantt Chart 8 to Gantt Chart 9
26 | Security Test | 2 days | 2015-02-08 | 2015-02-09 | 24 | 0$ | bar: Gantt Chart 8 to Gantt Chart 9
27 | Load Test | 1 day | 2015-02-10 | 2015-02-10 | 26 | 0$ | bar: Gantt Chart 10
28 | Stress Test | 1 day | 2015-02-10 | 2015-02-10 | 26 | 0$ | bar: Gantt Chart 10
29 | Acceptance Test | 1 day | 2015-02-11 | 2015-02-11 | 28 | 0$ | bar: Gantt Chart 11
30 | Request 3 person from finans department for user-end test | 1 day | 2015-02-12 | 2015-02-12 | 29 | 0$ | bar: Gantt Chart 12
31 | Request 3 person from hr department for user-end test | 1 day | 2015-02-12 | 2015-02-12 | 29 | 0$ | bar: Gantt Chart 12
32 | User-end Test | 2 days | 2015-02-16 | 2015-02-17 | 40 | 0$ | bar: Gantt Chart 16 to Gantt Chart 17
33 | End the software | 2 days | 2015-02-18 | 2015-02-19 | 32 | 0$ | bar: Gantt Chart 18 to Gantt Chart 19
34 | Give 3 people to Finans Department | 1 day | 2015-02-22 | 2015-02-22 | 33 | 0$ | bar: Gantt Chart 22
| Finans Department | 18 days | 2015-12-14 | 2015-03-05 |  | 100.000$
35 | Plan the salaries of the workers | 1 day | 2015-12-14 | 2015-12-14 | - | 90.000$ | bar: Gantt Chart 14
36 | Give the essential money for materials to hr department | 1 day | 2015-12-16 | 2015-12-16 | 3 | 90.000$ | bar: Gantt Chart 16
37 | Give 2 people to HR department | 1 day | 2015-12-16 | 2015-12-16 | 6 | 90.000$ | bar: Gantt Chart 16
38 | Give 2 people to software department | 1 day | 2015-12-25 | 2015-12-25 | 10 | 90.000$ | bar: Gantt Chart 25
39 | Give money to software department for computers | 1 day | 2015-12-25 | 2015-12-25 | 12 | 50.000$ | bar: Gantt Chart 25
40 | Give 3 people to software department | 1 day | 2015-02-15 | 2015-02-15 | 30 | 50.000$ | bar: Gantt Chart 15
41 | Request 3 people from the software department for the sale of the software | 1 day | 2015-02-22 | 2015-02-22 | 33 | 50.000$ | bar: Gantt Chart 22
42 | Give the salaries to workers | 1 day | 2015-12-24 | 2015-12-24 | 9 | 0$ | bar: Gantt Chart 24
43 | Sale the software | 10 days | 2015-02-23 | 2015-03-05 | 34 | 0$ | bar: Gantt Chart 23 to Gantt Chart 5
NOTE: | The whole budget is in the control of the finans department and the salaries are paid directly by the finans department to the workers